## Overview
Centene Forecasting — 5-Day Manual Test Plan
40 hours total ¦ 70% Testing (28h) ¦ 30% Bug Fix & Refactoring (12h)
Project Info
Project | Centene Forecasting
Roles Under Test | EDITOR & ADMIN
Test Period | 5 Days
Total Hours | 40h
Testing Time | 28h (5.6h/day)
Bug Fix Time | 12h (2.4h/day)
Priority Bug Areas | Edit/Allocation, Chat/Ramp Flows, File Uploads
Day-by-Day Schedule
Day | Focus Area | Modules | Test Cases | Testing Hours | Bug Fix Hours
Day 1 | Auth · Navigation · File Uploads · WebSocket | 4 | 25 | 5.6h | 2.4h
Day 2 | Data View · Cascade Filters · Download | 5 | 30 | 5.6h | 2.4h
Day 3 | Manager View · Execution Monitoring · Configuration | 6 | 35 | 5.6h | 2.4h
Day 4 ⭐ | Edit View · Bench Allocation · Target CPH · History Log [HIGH PRIORITY] | 6 | 30 | 5.6h | 2.4h
Day 5 ⭐ | Chat Assistant · CPH Update · All Ramp Flows [HIGH PRIORITY] | 10 | 40 | 5.6h | 2.4h
TOTAL |  |  | 160 | 28h | 12h
Status Legend |  | Priority Legend
Pass |  | High
Fail |  | Medium
Blocked |  | Low
Not Tested
In Progress

## Day1 - Auth & Upload
TC-ID | Module | Test Case Name | Priority | Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Bug-ID | Tested By | Tested On | Notes
TC-D1-001 | Authentication | Login with valid LDAP credentials | High | App running; valid LDAP user exists | 1. Navigate to /forecast_app/ 2. Enter valid username (AMERICAS\username) 3. Enter correct password 4. Click Login | User authenticated; redirected to timezone selection |  | Not Tested
TC-D1-002 | Authentication | Login with invalid password | High | App running | 1. Navigate to login page 2. Enter valid username 3. Enter wrong password 4. Click Login | Error message displayed; user stays on login page |  | Not Tested
TC-D1-003 | Authentication | Login with empty credentials | Medium | App running | 1. Navigate to login page 2. Leave username and password empty 3. Click Login | Validation error shown; login prevented |  | Not Tested
TC-D1-004 | Authentication | Login with missing AMERICAS\ prefix | Medium | App running | 1. Navigate to login page 2. Enter username without AMERICAS\ prefix 3. Enter password 4. Click Login | Authentication fails; error message shown |  | Not Tested
TC-D1-005 | Timezone | Select IST timezone | High | Logged in successfully | 1. Arrive at timezone selection page 2. Select Asia/Kolkata (IST) 3. Click Confirm | Session stores IST; redirected to upload/data view |  | Not Tested
TC-D1-006 | Timezone | Select CST timezone | Medium | Logged in successfully | 1. Arrive at timezone page 2. Select America/Chicago (CST) 3. Click Confirm | Session stores CST; redirected to data view |  | Not Tested
TC-D1-007 | Timezone | Select EST timezone | Medium | Logged in successfully | 1. Arrive at timezone page 2. Select America/New_York (EST) 3. Click Confirm | Session stores EST; redirected to data view |  | Not Tested
TC-D1-008 | Authentication | Logout clears session | High | Logged in as EDITOR | 1. Navigate to /forecast_app/logout/ 2. Try accessing a protected page | User logged out; redirected to login; protected pages inaccessible |  | Not Tested
TC-D1-009 | Permissions | EDITOR can access data view | High | EDITOR user logged in | 1. Login as EDITOR 2. Navigate to /forecast_app/data_view/ | Data view page loads successfully for EDITOR |  | Not Tested
TC-D1-010 | Permissions | EDITOR can access upload view | High | EDITOR user logged in | 1. Login as EDITOR 2. Navigate to /forecast_app/upload_view/ | Upload page loads successfully for EDITOR |  | Not Tested
TC-D1-011 | Permissions | ADMIN accesses cache management | High | ADMIN user logged in | 1. Login as ADMIN 2. Call /forecast_app/api/cache/clear/all/ | 200 response; cache cleared successfully |  | Not Tested
TC-D1-012 | Permissions | EDITOR blocked from admin-only endpoints | High | EDITOR user logged in | 1. Login as EDITOR 2. Call /forecast_app/api/cache/clear/all/ | 403 Forbidden response returned |  | Not Tested
TC-D1-013 | File Upload | Upload valid roster CSV | High | EDITOR logged in; valid roster.csv ready | 1. Navigate to upload view 2. Select file type = roster 3. Choose valid .csv file 4. Click Upload | File accepted; upload initiated; progress shown |  | Not Tested
TC-D1-014 | File Upload | Upload valid forecast Excel file | High | EDITOR logged in; valid forecast.xlsx ready | 1. Navigate to upload view 2. Select file type = forecast 3. Choose valid .xlsx file 4. Click Upload | File accepted; upload initiated successfully |  | Not Tested
TC-D1-015 | File Upload | Upload altered_forecast file | Medium | EDITOR logged in | 1. Navigate to upload view 2. Select file type = altered_forecast 3. Choose valid file 4. Click Upload | File accepted and processing initiated |  | Not Tested
TC-D1-016 | File Upload | Upload prod_team_roster file | Medium | EDITOR logged in | 1. Navigate to upload view 2. Select file type = prod_team_roster 3. Choose valid file 4. Click Upload | File accepted and processing initiated |  | Not Tested
TC-D1-017 | File Upload | Reject invalid file type (.txt) | High | EDITOR logged in | 1. Navigate to upload view 2. Select any upload type 3. Choose a .txt file 4. Click Upload | Error: only CSV and Excel files allowed |  | Not Tested
TC-D1-018 | File Upload | Reject invalid file type (.pdf) | High | EDITOR logged in | 1. Navigate to upload view 2. Select any upload type 3. Choose a .pdf file 4. Click Upload | Error: unsupported file type rejected |  | Not Tested
TC-D1-019 | File Upload | Upload progress tracking via API | High | File upload in progress | 1. Initiate file upload 2. Call /forecast_app/check_upload_progress/?file_upload_id=X 3. Inspect response | Response includes: progress (0-100), status, success fields |  | Not Tested
TC-D1-020 | File Upload | WebSocket real-time progress updates | High | File upload in progress | 1. Connect to /ws/up/ WebSocket 2. Initiate file upload 3. Monitor WebSocket messages | Real-time progress messages received (0 → 100) |  | Not Tested
TC-D1-021 | File Upload | Cache invalidated after forecast upload | High | Forecast file successfully uploaded | 1. Note current cached forecast data 2. Upload new forecast file 3. Reload data view | Fresh data loaded from FastAPI backend (cache cleared) |  | Not Tested
TC-D1-022 | Navigation | Top navigation menu visible | Medium | Logged in as EDITOR | 1. Navigate to any authenticated page 2. Check top navigation elements | Logo, user profile dropdown, and page links all visible |  | Not Tested
TC-D1-023 | Navigation | User profile shows name and timezone | Medium | Logged in with timezone selected | 1. Click user profile dropdown in top nav | Username, selected timezone, and logout link visible |  | Not Tested
TC-D1-024 | Navigation | Unauthenticated access redirects to login | High | Not logged in | 1. Navigate directly to /forecast_app/data_view/ without login | Redirected to login page with next= parameter |  | Not Tested
TC-D1-025 | Navigation | Chat widget visible on all pages | Low | Logged in as EDITOR | 1. Navigate to data view 2. Navigate to manager view 3. Navigate to edit view | Chat widget (bottom-right corner) visible on all authenticated pages |  | Not Tested

## Day2 - Data View
TC-ID | Module | Test Case Name | Priority | Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Bug-ID | Tested By | Tested On | Notes
TC-D2-001 | Data Type | Select Roster data type | High | Logged in; data available | 1. Navigate to /forecast_app/data_view/ 2. Select Roster from data type selector | Roster-specific filter chain loads (no worktype filter) |  | Not Tested
TC-D2-002 | Data Type | Select Forecast data type | High | Logged in; data available | 1. Navigate to data view 2. Select Forecast from data type selector | Full cascade filter chain loads including worktype |  | Not Tested
TC-D2-003 | Data Type | Select Prod Team Roster | Medium | Logged in | 1. Navigate to data view 2. Select Prod Team Roster | Prod team roster filter chain loads |  | Not Tested
TC-D2-004 | Data Type | Select Summary data type | Medium | Logged in | 1. Navigate to data view 2. Select Summary | Summary filter options load |  | Not Tested
TC-D2-005 | Cascade Filters | Year filter loads available years | High | Forecast type selected | 1. Select Forecast data type 2. Open year dropdown | Available forecast years listed (e.g., 2024, 2025) |  | Not Tested
TC-D2-006 | Cascade Filters | Month filter populates after year selection | High | Year selected | 1. Select year 2024 2. Open month dropdown | Only months with data for selected year shown |  | Not Tested
TC-D2-007 | Cascade Filters | Platform filter populates after month selection | High | Year and month selected | 1. Select year 2. Select month 3. Open platform dropdown | Platforms available for selected year+month shown |  | Not Tested
TC-D2-008 | Cascade Filters | Market filter populates after platform selection | High | Year, month, platform selected | 1. Select year, month, platform 2. Open market dropdown | Markets for selected platform shown |  | Not Tested
TC-D2-009 | Cascade Filters | Locality filter includes All option | Medium | Year through market selected | 1. Select year through market 2. Open locality dropdown | Options shown including 'All' option |  | Not Tested
TC-D2-010 | Cascade Filters | Worktype filter populates last | High | All prior filters selected | 1. Complete all prior selections 2. Open worktype dropdown | Worktypes available for all selected filters shown |  | Not Tested
TC-D2-011 | Cascade Filters | Changing year resets downstream filters | High | All filters selected | 1. Select all filters 2. Change year selection | Month, platform, market, locality, worktype reset |  | Not Tested
TC-D2-012 | Cascade Filters | Missing year shows validation error | Medium | Data view open | 1. Skip year selection 2. Try to load data without year | Validation error: year is required |  | Not Tested
TC-D2-013 | Cascade Filters | Select2 searchable dropdown works | Medium | Filter dropdown open | 1. Open platform dropdown 2. Type partial platform name in search box | Filtered options shown matching search text |  | Not Tested
TC-D2-014 | Cascade Filters | Filter APIs return correct data per step | High | Network tab open in browser dev tools | 1. Monitor network calls during filter selection 2. Check /forecast_app/forecast/months/ etc. | Each API call returns correctly filtered options for selections made |  | Not Tested
TC-D2-015 | Cascade Filters | Empty result state handled gracefully | Medium | Filters with no data selected | 1. Select combination with no available data 2. Check dropdown result | 'No options available' shown; no JS error thrown |  | Not Tested
TC-D2-016 | Cascade Filters | Backend unavailable shows graceful error | High | FastAPI backend stopped | 1. Stop FastAPI backend at 127.0.0.1:8888 2. Open filter dropdown | User-friendly error message shown; no unhandled exception |  | Not Tested
TC-D2-017 | Roster Table | Roster data displays in DataTable | High | Roster filters selected | 1. Select all roster filters 2. Click Load/Apply | Roster records shown in DataTable with pagination controls |  | Not Tested
TC-D2-018 | Roster Table | Roster table pagination works | Medium | Roster data loaded | 1. Load roster data 2. Click Next Page button | Next page of records loaded correctly |  | Not Tested
TC-D2-019 | Forecast Table | Forecast data multi-tab per LOB | High | Forecast filters selected | 1. Select forecast filters 2. Load data | Tabs created per main_lob+worktype combination; data in each tab |  | Not Tested
TC-D2-020 | Forecast Table | Forecast table server-side pagination | High | Forecast data loaded | 1. Load large forecast dataset 2. Navigate between pages | Server-side pagination works; no full page reload |  | Not Tested
TC-D2-021 | Forecast Table | DataTable search and sort work | Medium | Data loaded | 1. Load data 2. Use search box 3. Click column headers to sort | Search filters rows; sort reorders columns correctly |  | Not Tested
TC-D2-022 | Actuals Table | Actuals data displays | Medium | Actuals data available | 1. Navigate to actuals view 2. Set filters (month, boc, locality, process) 3. Load data | Actual performance data shown in table |  | Not Tested
TC-D2-023 | Forecast Table | Inline editing via DataTables Editor | High | EDITOR logged in; forecast data loaded | 1. Click on editable cell in forecast table 2. Modify value 3. Save | Value updated in backend; table refreshes with new value |  | Not Tested
TC-D2-024 | Data View | Empty data set shows friendly message | Medium | Filters with no matching data | 1. Select filters producing no data 2. Load table | 'No records found' message displayed; no error |  | Not Tested
TC-D2-025 | Download | Download roster data as CSV | High | Roster data loaded | 1. Load roster data 2. Click Download button 3. Select CSV format | CSV file downloaded with correct data |  | Not Tested
TC-D2-026 | Download | Download roster data as Excel | Medium | Roster data loaded | 1. Load roster data 2. Click Download 3. Select Excel format | .xlsx file downloaded successfully |  | Not Tested
TC-D2-027 | Download | Download forecast data | High | Forecast data loaded | 1. Load forecast data 2. Click Download | Forecast file downloaded with correct data |  | Not Tested
TC-D2-028 | Download | Downloaded file has correct MIME type | Medium | Download initiated | 1. Initiate download 2. Check response headers in browser | Content-Type matches format (text/csv or application/vnd.openxmlformats) |  | Not Tested
TC-D2-029 | Download | Download with no data shows error | Medium | No data loaded | 1. Try to download without loading data first | Error message: no data available to download |  | Not Tested
TC-D2-030 | Download | Downloaded filename follows naming convention | Low | Download initiated | 1. Download any data file 2. Check filename | Filename includes data type and date (e.g., roster_2025-04.csv) |  | Not Tested

## Day3 - Dashboards
TC-ID | Module | Test Case Name | Priority | Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Bug-ID | Tested By | Tested On | Notes
TC-D3-001 | Manager View | Manager view page loads | High | EDITOR logged in | 1. Navigate to /forecast_app/manager-view/ | Page loads with category hierarchy and 6-month forecast data |  | Not Tested
TC-D3-002 | Manager View | Report month selector works | High | Manager view open | 1. Open report month dropdown 2. Select a different month | Data refreshes and displays for the selected month |  | Not Tested
TC-D3-003 | Manager View | Category filter filters data | High | Manager view open | 1. Select specific category (e.g., amisys-onshore) | Data filtered to show only selected category hierarchy |  | Not Tested
TC-D3-004 | Manager View | 6 months of data displayed | Medium | Manager view open | 1. Load manager view 2. Count forecast month columns | Exactly 6 months displayed (MONTHS_TO_DISPLAY=6 config) |  | Not Tested
TC-D3-005 | Manager View | KPI cards display correctly | High | Manager view loaded | 1. Load manager view 2. Check KPI summary cards at top | Cards show capacity utilization, forecast accuracy, staffing levels |  | Not Tested
TC-D3-006 | Manager View | Invalid report_month returns 400 | Medium | Manager view API accessible | 1. Call /api/manager-view/data/ with report_month=invalid 2. Check response | 400 Bad Request response with error message |  | Not Tested
TC-D3-007 | Manager View | Manager view data cached 900s | Medium | ADMIN logged in; manager view loaded | 1. Load manager view 2. Check /api/cache/stats/ | Manager view data in cache with ~900s TTL |  | Not Tested
TC-D3-008 | Manager View | Missing report_month param returns error | Medium | Manager view API accessible | 1. Call /api/manager-view/data/ without report_month param | Error response indicating report_month is required |  | Not Tested
TC-D3-009 | Execution Monitor | Execution list page loads | High | ADMIN logged in | 1. Navigate to /forecast_app/execution-monitoring/ | List of file upload executions shown with filters |  | Not Tested
TC-D3-010 | Execution Monitor | Filter executions by status | High | Execution list open | 1. Select status filter = SUCCESS 2. Apply filter | Only SUCCESS status executions shown |  | Not Tested
TC-D3-011 | Execution Monitor | Filter executions by month/year | Medium | Execution list open | 1. Select month and year filters 2. Apply | Executions for the selected period shown |  | Not Tested
TC-D3-012 | Execution Monitor | Filter by uploaded_by user | Medium | Execution list open | 1. Enter username in uploaded_by filter 2. Apply | Executions uploaded by that user shown |  | Not Tested
TC-D3-013 | Execution Monitor | Execution list pagination works | Medium | Many executions exist | 1. Load execution list 2. Click Next Page | Next page of records loaded correctly |  | Not Tested
TC-D3-014 | Execution Monitor | Execution details show for completed | High | Completed execution exists | 1. Click on a completed execution 2. View details panel | Detailed logs, timing info, and status shown |  | Not Tested
TC-D3-015 | Execution Monitor | In-progress execution refreshes every 5s | High | In-progress upload exists | 1. Initiate file upload 2. Open execution details | Details auto-refresh approximately every 5s (5s cache TTL) |  | Not Tested
TC-D3-016 | Execution Monitor | Download execution summary report | High | Completed execution exists | 1. Click download on a completed execution 2. Select 'summary' report type | Summary report file downloaded successfully |  | Not Tested
TC-D3-017 | Execution Monitor | KPIs show success rate and counts | Medium | Executions exist | 1. Load execution monitoring page 2. Check KPI section | Success rate %, failed count, pending count all shown |  | Not Tested
TC-D3-018 | Month Config | Month config list loads | High | ADMIN logged in | 1. Navigate to /forecast_app/configuration/ 2. Select Month Configuration tab | Existing month configurations listed |  | Not Tested
TC-D3-019 | Month Config | Filter config list by month | Medium | Configuration list open | 1. Apply month name filter 2. Check results | Only configs for that month shown |  | Not Tested
TC-D3-020 | Month Config | Create new month configuration | High | ADMIN logged in | 1. Click Create 2. Fill month, year, work_type fields 3. Submit | New config created; appears in list |  | Not Tested
TC-D3-021 | Month Config | Update existing month config | High | Config record exists | 1. Click Edit on a config 2. Modify fields 3. Save | Config updated successfully |  | Not Tested
TC-D3-022 | Month Config | Delete month config (admin only) | High | ADMIN logged in; config exists | 1. Click Delete on a config 2. Confirm deletion | Config deleted; removed from list |  | Not Tested
TC-D3-023 | Month Config | Bulk create month configs | Medium | ADMIN logged in | 1. Prepare array of config objects 2. POST to bulk create endpoint | All configs created in batch; count confirmed |  | Not Tested
TC-D3-024 | Month Config | Validate endpoint catches errors pre-save | Medium | Config form open | 1. Call validate endpoint with invalid data | Validation errors returned before save attempted |  | Not Tested
TC-D3-025 | Month Config | Duplicate config prevention | Medium | Config exists | 1. Try to create duplicate month+year+work_type config | Error: duplicate configuration not allowed |  | Not Tested
TC-D3-026 | Month Config | Required field validation on create | Medium | Create config form | 1. Submit create form with missing required fields | Validation error listing each missing field |  | Not Tested
TC-D3-027 | CPH Config | Target CPH config list loads | High | Configuration page open | 1. Navigate to configuration 2. Select Target CPH tab | All CPH configurations listed in table |  | Not Tested
TC-D3-028 | CPH Config | Create new CPH configuration | High | ADMIN logged in | 1. Click Create 2. Fill main_lob, case_type, target_value 3. Submit | New CPH config created; appears in list |  | Not Tested
TC-D3-029 | CPH Config | Update CPH target value | High | CPH config exists | 1. Click Edit on CPH config 2. Change target_value 3. Save | CPH value updated successfully |  | Not Tested
TC-D3-030 | CPH Config | Delete CPH configuration | High | ADMIN logged in | 1. Click Delete on CPH config 2. Confirm | Config deleted from list |  | Not Tested
TC-D3-031 | CPH Config | Bulk create CPH configs | Medium | ADMIN logged in | 1. POST array of CPH objects to bulk endpoint | All CPH configs created in batch |  | Not Tested
TC-D3-032 | CPH Config | Distinct main LOBs endpoint | Medium | CPH configs exist | 1. Call /api/configuration/target-cph/distinct/main-lobs/ | Unique main LOB list returned correctly |  | Not Tested
TC-D3-033 | CPH Config | Distinct case types endpoint | Medium | CPH configs exist | 1. Call /api/configuration/target-cph/distinct/case-types/ | Unique case type list returned correctly |  | Not Tested
TC-D3-034 | CPH Config | Cache stats accessible to ADMIN | High | ADMIN logged in | 1. Call /forecast_app/api/cache/stats/ | Cache backend, TTLs, key counts returned |  | Not Tested
TC-D3-035 | CPH Config | Clear cascade cache endpoint | High | ADMIN logged in | 1. Call /forecast_app/api/cache/clear/cascade/ | Cascade filter caches cleared; 200 response |  | Not Tested

## Day4 - Edit & Alloc
TC-ID | Module | Test Case Name | Priority | Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Bug-ID | Tested By | Tested On | Notes
TC-D4-001 | Edit View | Edit view page loads with tabs | High | EDITOR logged in | 1. Navigate to /forecast_app/edit-view/ | Page loads with Bench Allocation and History Log tabs visible |  | Not Tested
TC-D4-002 | Edit View | Bench Allocation tab active by default | Medium | Edit view open | 1. Open edit view 2. Observe default tab | Bench Allocation tab is active by default |  | Not Tested
TC-D4-003 | Edit View | Allocation reports dropdown populated | High | Edit view open | 1. Open allocation reports dropdown | Available report periods (month/year combinations) listed |  | Not Tested
TC-D4-004 | Edit View | Switch to History Log tab | Medium | Edit view open | 1. Click History Log tab | History log content loads in tab |  | Not Tested
TC-D4-005 | Edit View | EDITOR role can access edit view | High | EDITOR logged in | 1. Login as EDITOR 2. Navigate to /forecast_app/edit-view/ | Edit view accessible; edit actions available for EDITOR |  | Not Tested
TC-D4-006 | Bench Allocation | Preview allocation for valid month/year | High | EDITOR logged in | 1. Select valid month and year 2. Click Preview | Preview card shown with projected allocation data and impact |  | Not Tested
TC-D4-007 | Bench Allocation | Preview allocation for invalid date format | High | Edit view open | 1. Enter invalid date in month/year 2. Click Preview | Error message: invalid date format returned |  | Not Tested
TC-D4-008 | Bench Allocation | Update single LOB allocation | High | EDITOR logged in; preview shown | 1. Preview allocation 2. Modify single LOB value 3. Submit update | Single LOB allocation updated in backend successfully |  | Not Tested
TC-D4-009 | Bench Allocation | Update multiple LOBs in one submission | High | EDITOR logged in | 1. Modify multiple LOB values 2. Submit bulk update | All LOB allocations updated atomically |  | Not Tested
TC-D4-010 | Bench Allocation | Validation on negative allocation value | Medium | Allocation form open | 1. Enter negative value for allocation 2. Submit | Validation error: allocation must be non-negative |  | Not Tested
TC-D4-011 | Bench Allocation | Validation on non-numeric allocation | Medium | Allocation form open | 1. Enter text in allocation field 2. Submit | Validation error: allocation must be numeric |  | Not Tested
TC-D4-012 | Bench Allocation | Audit trail created on allocation update | High | EDITOR logged in | 1. Update allocation 2. Navigate to History Log tab | Change recorded with user, timestamp, old and new values |  | Not Tested
TC-D4-013 | Bench Allocation | Available change types endpoint responds | Medium | ADMIN logged in | 1. Call /api/edit-view/available-change-types/ | List of supported change types returned |  | Not Tested
TC-D4-014 | Target CPH | View current CPH targets in edit view | High | EDITOR logged in | 1. Open edit view 2. Navigate to CPH section | Current CPH values for each LOB/case type shown |  | Not Tested
TC-D4-015 | Target CPH | Preview CPH change impact | High | CPH data loaded; row selected | 1. Enter new CPH value 2. Click Preview | Preview card shows old→new CPH and impact per month (FTE/Capacity/Gap) |  | Not Tested
TC-D4-016 | Target CPH | Update CPH value via edit view | High | EDITOR logged in | 1. Preview CPH change 2. Confirm update | CPH updated in backend; forecast data refreshes |  | Not Tested
TC-D4-017 | Target CPH | CPH validation: zero or negative rejected | High | CPH form open | 1. Enter CPH = 0 or negative value 2. Submit | Validation error: CPH must be greater than 0 |  | Not Tested
TC-D4-018 | Target CPH | CPH validation: text value rejected | Medium | CPH form open | 1. Enter non-numeric text in CPH field 2. Submit | Validation error: CPH must be a number |  | Not Tested
TC-D4-019 | Target CPH | CPH change reflected in forecast table | High | CPH updated successfully | 1. Update CPH 2. Navigate to forecast table 3. Check FTE Required column | FTE Required recalculated with new CPH value |  | Not Tested
TC-D4-020 | Reallocation | Forecast reallocation filters load | High | EDITOR logged in | 1. Navigate to forecast reallocation section 2. Load filters | Filter dropdowns for reallocation populate correctly |  | Not Tested
TC-D4-021 | Reallocation | Reallocation data loads for selected filters | High | Filters selected | 1. Select reallocation filters 2. Load data | Reallocation data shown for selected filter combination |  | Not Tested
TC-D4-022 | Reallocation | Preview reallocation impact | High | Data loaded | 1. Modify allocation values 2. Click Preview | Impact of reallocation shown before saving |  | Not Tested
TC-D4-023 | Reallocation | Update reallocation values | High | Preview shown and verified | 1. Preview reallocation 2. Confirm update | Reallocation saved to backend successfully |  | Not Tested
TC-D4-024 | Reallocation | Invalid reallocation values rejected | Medium | Reallocation form open | 1. Enter invalid values in reallocation fields 2. Try to submit | Validation errors shown for each invalid field |  | Not Tested
TC-D4-025 | History Log | History log displays all changes | High | Allocation changes previously made | 1. Navigate to History Log tab | List of all allocation changes shown with timestamps |  | Not Tested
TC-D4-026 | History Log | Filter history by date range | Medium | History log open with entries | 1. Set from/to date filter 2. Apply | Changes within date range shown; outside range excluded |  | Not Tested
TC-D4-027 | History Log | Filter history by user | Medium | History log open | 1. Filter by specific username 2. Apply | Only changes by that user shown |  | Not Tested
TC-D4-028 | History Log | Filter history by change type | Medium | History log open | 1. Select change type filter 2. Apply | Only changes of selected type shown |  | Not Tested
TC-D4-029 | History Log | History log pagination works | Medium | Many history records exist | 1. Load history log 2. Navigate between pages | Pagination works correctly; all records accessible |  | Not Tested
TC-D4-030 | History Log | Download history as Excel | High | EDITOR logged in; history entries exist | 1. Click Download on history entry | Excel file with change details downloaded with correct filename |  | Not Tested

## Day5 - Chat & Ramp
TC-ID | Module | Test Case Name | Priority | Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Bug-ID | Tested By | Tested On | Notes
TC-D5-001 | Chat Widget | Chat widget visible and opens | High | Logged in as EDITOR | 1. Navigate to any page 2. Click chat widget in bottom-right corner | Chat panel opens showing conversation interface |  | Not Tested
TC-D5-002 | Chat Widget | Chat widget minimizes | Medium | Chat open | 1. Click minimize button in chat header | Chat minimized; unread badge visible if new messages |  | Not Tested
TC-D5-003 | Chat Widget | Start new conversation | High | Chat open with existing history | 1. Click New Conversation button | Previous messages cleared; fresh context started |  | Not Tested
TC-D5-004 | Chat Widget | WebSocket connection status indicator | Medium | Chat open | 1. Open chat panel 2. Check connection status indicator | Connected status shown (green indicator or similar) |  | Not Tested
TC-D5-005 | Chat Widget | Chat disconnects gracefully on logout | Medium | Chat open | 1. Log out while chat is open | WebSocket connection closed cleanly; no JS errors |  | Not Tested
TC-D5-006 | get_available_reports | List available forecast reports | High | Chat open | 1. Type: 'What forecast data do you have?' | Card shown with available report periods labeled Current/Outdated |  | Not Tested
TC-D5-007 | propose_data_fetch | Confirmation card shown before data fetch | High | Chat open | 1. Type: 'Show forecast for March 2025' | Confirmation card with month, filters, and Fetch/Cancel buttons displayed |  | Not Tested
TC-D5-008 | confirm_forecast_fetch | Forecast table renders after confirmation | High | Confirmation card shown | 1. Click 'Yes Fetch Data' button | Forecast table with multi-column headers rendered in chat |  | Not Tested
TC-D5-009 | get_forecast_data | Filter by platform in forecast query | High | Forecast data loaded | 1. Type: 'Show data for Amisys platform' | Data filtered to Amisys platform only |  | Not Tested
TC-D5-010 | get_forecast_data | Filter by state in forecast query | High | Forecast data loaded | 1. Type: 'Show data for California only' | Data filtered to CA state only |  | Not Tested
TC-D5-011 | get_forecast_data | Show totals only option | Medium | Forecast data loaded | 1. Type: 'Show totals for March' | Only aggregated totals row shown (not individual records) |  | Not Tested
TC-D5-012 | get_forecast_data | Gap column is color-coded | High | Forecast table rendered in chat | 1. Load forecast table 2. Check Gap column values | Negative gap = red background; positive gap = green background |  | Not Tested
TC-D5-013 | get_fte_details | FTE details for selected row | High | Forecast table shown with row selected | 1. Click a forecast row to select it 2. Type: 'Show FTE details' | FTE breakdown card with monthly components shown |  | Not Tested
TC-D5-014 | update_filters | Extend filters (add to existing) | High | Some filters already set | 1. Type: 'Also show Texas data' | TX state added to existing state filters (extend operation) |  | Not Tested
TC-D5-015 | update_filters | Replace filters (overwrite existing) | High | Filters set | 1. Type: 'Show only Florida data' | All state filters replaced with FL only (replace operation) |  | Not Tested
TC-D5-016 | update_filters | Reset all filters | Medium | Filters set | 1. Type: 'Reset filters' | All filters cleared except month/year context |  | Not Tested
TC-D5-017 | clear_context | Full context clear | High | Context has filters and selected row | 1. Type: 'Clear everything' | All filters, selected row, and cached data cleared from context |  | Not Tested
TC-D5-018 | preview_cph_change | Preview CPH set_to operation | High | Forecast row selected in chat | 1. Select row 2. Type: 'Change CPH to 50' | Preview card with old→new CPH and per-month impact shown |  | Not Tested
TC-D5-019 | preview_cph_change | Preview CPH increase by percentage | High | Row selected | 1. Type: 'Increase CPH by 10%' | Preview showing 10% increase calculation and new values |  | Not Tested
TC-D5-020 | preview_cph_change | Preview CPH decrease by percentage | Medium | Row selected | 1. Type: 'Decrease CPH by 5%' | Preview showing 5% decrease calculation |  | Not Tested
TC-D5-021 | preview_cph_change | CPH validation: negative value rejected | High | Row selected | 1. Type: 'Set CPH to -10' | Error card: CPH must be a positive number |  | Not Tested
TC-D5-022 | confirm_cph_update | CPH change applied after confirmation | High | CPH preview card shown | 1. Click Confirm Change button in preview card | Success card: CPH changed from X to Y; data refreshed |  | Not Tested
TC-D5-023 | setup_ramp_calculation | Ramp trigger card displayed | High | Forecast row selected in chat | 1. Select a row 2. Type: 'Set up ramp for March 2026' | Ramp trigger card with week count and Configure Ramp button shown |  | Not Tested
TC-D5-024 | Ramp Modal | Ramp configuration modal opens | High | Ramp trigger card shown | 1. Click Configure Ramp button | Modal opens with week table (Week 1-4 with working days pre-filled) |  | Not Tested
TC-D5-025 | Ramp Submit | Submit ramp week data | High | Ramp modal open | 1. Fill rampPercent and rampEmployees per week 2. Click Submit | Ramp confirmation card with per-week summary table shown |  | Not Tested
TC-D5-026 | Ramp Preview | Confirm ramp to get preview diff | High | Ramp confirmation card shown | 1. Click Yes Proceed button | Ramp preview card with Current vs Projected vs Change columns shown |  | Not Tested
TC-D5-027 | Ramp Apply | Apply ramp successfully | High | Ramp preview card shown | 1. Click Confirm Apply button | Success card 'Ramp Applied Successfully'; ramp state cleared from context |  | Not Tested
TC-D5-028 | Ramp Validation | Invalid ramp percentage rejected | Medium | Ramp modal open | 1. Enter rampPercent = 150 (over 100) 2. Click Submit | Validation error: ramp% must be between 0 and 100 |  | Not Tested
TC-D5-029 | get_applied_ramp | Show existing applied ramps | High | Ramps previously applied for a row | 1. Select row 2. Type: 'Show ramp for March 2026' | Ramp list card with ramp names, peak employees, and Show Data button |  | Not Tested
TC-D5-030 | Bulk Ramp Modal | Bulk edit modal opens from ramp list | High | Ramp list card shown | 1. Click Show Data button in ramp list card | Bulk edit modal opens with all existing ramps in editable table |  | Not Tested
TC-D5-031 | Bulk Ramp Submit | Submit edited bulk ramps | High | Bulk modal open with edits made | 1. Modify ramp values 2. Click Submit | Bulk confirmation card with ramp-by-ramp summary shown |  | Not Tested
TC-D5-032 | Bulk Ramp Preview | Bulk ramp preview diff | High | Bulk confirmation card shown | 1. Click Yes Preview Changes | Bulk preview card: Before/After/Change for FTE and Capacity |  | Not Tested
TC-D5-033 | Bulk Ramp Apply | Bulk apply with partial success handling | High | Bulk preview card shown | 1. Click Confirm Apply | Result card shows: applied count, failed count, error reasons for any failures |  | Not Tested
TC-D5-034 | setup_ramp_campaign | Campaign entry card shown | High | Forecast data loaded in chat context | 1. Type: 'Open campaign manager' | Campaign entry card with LOB count, months count, Open Campaign Manager button |  | Not Tested
TC-D5-035 | Campaign Modal | Campaign manager modal opens in Entry view | High | Campaign entry card shown | 1. Click Open Campaign Manager button | Campaign modal opens in Entry view showing LOB/month grid |  | Not Tested
TC-D5-036 | Campaign Stage | Stage LOBs and months for campaign | High | Campaign modal in Entry view | 1. Select LOBs and months 2. Fill ramp data per combo 3. Click Submit All | Preview view shows staged rows with parallel API preview results |  | Not Tested
TC-D5-037 | Campaign Preview | Campaign preview shows all staged rows | High | Campaign modal in Preview view | 1. Check preview table in modal | All LOB+month combos shown with FTE delta, Capacity delta columns |  | Not Tested
TC-D5-038 | Campaign Apply | Apply all campaign ramps | High | Campaign modal in Preview view | 1. Click Confirm Apply All | Result view: X applied, Y failed; campaign state cleared from context |  | Not Tested
TC-D5-039 | Error Handling | CPH preview without row selected shows error | High | No forecast row selected | 1. Type: 'Change CPH to 50' without selecting a row | Error card: 'Please select a forecast row first' |  | Not Tested
TC-D5-040 | Error Handling | Context persists across conversation turns | High | Filters and row selected | 1. Set filters and select row 2. Send 3+ more messages 3. Verify context | Month, year, filters, and selected row still maintained in context |  | Not Tested

## Bug Tracker
Bug-ID | Date Found | Day | Module | Severity | Status | Description | Steps to Reproduce | Expected Behavior | Actual Behavior | Fixed On | Fixed By | Notes
BUG-001
BUG-002
BUG-003

## Test Report
Centene Forecasting — Test Execution Report
Auto-calculated from Day 1-5 sheets ¦ Update Status column in each day sheet to see results refresh
SECTION 1: Daily Test Execution Summary
Day | Focus Area | Total TCs | Pass | Fail | Blocked | Not Tested | Pass % | Bug-Fix Hours
Day 1 | Auth · Navigation · File Uploads · WebSocket | 25 | [5 empty] | 2.4h
Day 2 | Data View · Cascade Filters · Download | 30 | [5 empty] | 2.4h
Day 3 | Manager View · Execution Monitoring · Configuration | 35 | [5 empty] | 2.4h
Day 4 ⭐ | Edit View · Bench Allocation · Target CPH · History Log | 30 | [5 empty] | 2.4h
Day 5 ⭐ | Chat Assistant · CPH Update · All Ramp Flows | 40 | [5 empty] | 2.4h
TOTAL | All 5 Days | [6 empty] | 12h
SECTION 2: Bug Severity Breakdown
Severity | Count | % of Total
Critical
High
Medium
Low
TOTAL
SECTION 3: Test Summary Metrics
Total Test Cases | 160
Total Testing Hours | 28h
Total Bug Fix Hours | 12h
Roles Tested | EDITOR & ADMIN
Priority Bug Areas | Edit/Allocation, Chat/Ramp Flows, File Uploads
SECTION 4: High Priority Areas Status
Day | Area | Total TCs | Pass | Fail | Pass %
Day 4 ⭐ | Edit View & Allocation Features
Day 5 ⭐ | Chat Assistant & Ramp Flows